## Slide 1: Significant Changes in the Standard AIA Documents
James R. Case 500 Woodward Ave., Suite 2500 Detroit, MI 48226 313-961-0200 jcase@kerr-russell.com

## Slide 2: B101-Article 1-Initial Information
“Initial Information” is now in the body of the Agreement as compared to adding an “Exhibit A”
  1.1.1 – Program
  1.1.2 – Physical Characteristics: size, location, geotech reports, topo surveys, etc.
  1.1.3 – Budget
  1.1.4 – Design/Construction Milestones Schedule
    .1 Design Milestone
    .2 Construction Commencement
    .3 Substantial Completion
    .4 Other

## Slide 3
  1.1.5 – Procurement/Delivery Method
  1.1.6 – Sustainable Objective for Project - Use of E204, Sustainable Project Objective
    Does not carry over automatically in C401
  1.1.9 – Specific Listing of Owner Provided Consultants
  1.1.11.1 – List of Architect Provided Consultants as Part of “Basic Services” (See Article 4)
  1.1.11.2 – List of Consultants Provided under “Supplemental Services” (See Article 4)
  1.1.12 – “Other” Initial Information

## Slide 4
  1.2 – Recognition that Initial Information can change, but addition of new clause specifically indicates that for “material change” the Owner shall adjust:
    Budget
    Design/Construction Milestones
  1.3 – Digital Data Protocol (if any) is agreed upon; requires use of E203-2013
    If the form is not used, any BIM information is utilizing at party’s own risk
      This is carried over to the C401 (1.10)

## Slide 5: B101-Article 2-Architect’s Responsibilities
2.1 – New representation that Architect and/or Consultant performing services is licensed
2.5 – Insurance information (coverages/amounts) is now listed
  Can meet GL and Auto requirements with umbrella policies as long as such policies are not more restrictive (2.5.3)
  Coverages now must apply to ongoing and completed operations
    Talk to Brett

## Slide 6: B101-Article 3-Scope of Architect’s Basic Services
3.1.4 – Specifically excludes responsibility for Owner’s acceptance of non-conforming work unless Architect provides written approval
3.2 – Schematic Design Phase
  Still have to consider and discuss Owner’s program, budget, schedule, proposed procurement and delivery method with Owner and reach agreement on same (3.2.1 through 3.2.4)
  Now must consider sustainable design
    Will need to strike this provision if not applicable
3.3 – Design Development Phase
  No significant changes

## Slide 7
3.4 – Construction Document Phase
  No significant changes other than indicating that performance criteria must be detailed (see 3.4.1)
    Strike if not applicable
3.5 – Bidding Phase is Now the “Procurement” Phase
  Only significant change is that consideration of Contractor Substitutions is now specifically stated to be an “Additional Service”

## Slide 8
3.6 – Construction Phase Services. Only significant changes are to:
  (a) Correlate Architect’s Obligation to review design professional services provided by Contractor with Article 3.12.10 of A201 (See 3.6.4.3)
  (b) Attempts to make it absolutely clear that Architect is never responsible for safety aspects of means, methods, techniques or sequences of construction (Deletes “unless specifically stated by Architect”) (See 3.6.4.2)
  (c) Makes clear certification of Contractor’s final pay applicable is not a warranty (See 3.6.6.1)

## Slide 9: B101-Article 4-Supplemental and Additional Services
Attempt has been made to recognize that certain services may be required for the Project which cannot be definitively stated as necessary when contract is formulated.
Different method of compensation is required for Supplemental Services (See 11.2)
List of services is provided and whether these will be performed by Architect, Owner or “not provided” and must be filled in.
Specifically states that unless otherwise addressed, the service will not be provided (meaning that if it is, it will be an “Additional Service” paid per Article 11.3).

## Slide 10
4.1.2.1 and 4.1.2.2 will cause confusion, as these provisions require the parties to set forth the Supplemental Services each will perform.
  Inevitably, items checked in 4.1.1.1 list will be omitted in 4.1.2 statements.
4.1.3 – Provides that “Sustainable Design” services are Supplemental Services
  But, if Architect is required to consider such services per 3.2.5.1, how can this work be a “Supplemental Service”?
  Completing this section of the Contract will take considerable thought and effort.

## Slide 11
4.2 – Additional Services, is relatively similar, but for new provision (4.2.1.3) that indicates a change required due to a code interpretation different than previously made by code officials or an interpretation contrary to what is called for by instruments of service prepared in accordance with the standard of care is now an Additional Service.

## Slide 12: B101-Article 5-Owner’s Responsibilities
No significant modifications

## Slide 13: B101-Article 6-Cost of the Work
One significant modification:
  There is now recognition that if modifications to the Contract Documents are required because low bid or negotiated price exceeds budget due to market conditions that could not be reasonably anticipated, the work will be performed (and paid for) as an Additional Service (See Article 6.7)

## Slide 14: B101-Article 7-Copyrights and Licenses
No significant changes

## Slide 15: B101-Article 8-Claims and Disputes
No significant changes

## Slide 16: B101-Article 9-Termination or Suspension
One significant change:
  In termination for convenience situations, the parties are now to negotiate a termination fee and/or continued use of documents licensing fee, in addition to pre-termination costs.

## Slide 17: B101-Article 10-Miscellaneous Provisions
Adds a clause specifying when confidential information may be disclosed (new Section10.8.1) and a “savings” clause (new Section 10.9)

## Slide 18: B101-Article 11-Compensation
Includes some fairly significant modifications.
11.1 - Now includes specific subsection indicating whether fee is a Stipulated Sum, percentage of the Owner’s Budget for Cost of the Work (which per Article 11.6 are based on Owner’s most recent budget at time progress payments are made with no adjustment made for prior payments based on earlier budget), or some other basis.
11.2 – Insert payment terms for “Supplemental Services”
11.3 – Insert payment terms for “Additional Services”
11.8.1.11 and 11.10.1.2 allow for various payments if sustainable design is included

## Slide 19: B101-Article 12-Special Terms and Conditions
Still needs to be completed if applicable and deleted if not.

## Slide 20: B101-Article 13-Scope of Agreement
13.2.2 – Still includes E203-2013, BIM and Digital Data Exhibit, as part of the Agreement
  Need to make sure this is applicable.
13.2.3 – Provides a box to check for E204-2017, the “Sustainable Projects Exhibit”
  Best to delete if not applicable.

## Slide 21: C401-Article 1-General Provisions
1.2 – Fully set forth portion of Architect’s scope Consultant will perform.
1.3 – Incorporation by reference/assumption of obligations/rights

## Slide 22: C401-Article 2-Consultant Responsibilities
2.1 – Standard of Care is based on standard of care in Owner/Architect Agreement.
2.3 – Has to recommend appropriate studies, tests, etc.
  New requirement that Consultant must inform Architect if Consultant requires additional information
2.8 – Insurance policies/limits are now fill in the blank

## Slide 23: C401-Article 3-Consultant’s Scope of Services
3.1 – Have to phase and sequence per direction of Architect
3.1.1 – Contemplates site visits

## Slide 24: C401-Articles 4-5
Article 4: Additional Services
  Are provided when required in writing and compensated as set forth in Article 11.2
Article 5: Architect’s Responsibilities
  Only significant addition is Architect, after receipt of written request, has to provide information to Consultant which will allow Consultant to enforce lien rights

## Slide 25: C401: Articles 6-8
Article 6: Cost of the Work
  Must prepare cost estimates for Architect associated with Consultant’s scope
Article 7: Copyrights and Licenses
  No changes
Article 8: Claims and Disputes
  8.1.1 – In essence makes Owner related disputes subject to Owner/Architect dispute resolution, and makes Architect/Consultant disputes subject to mediation and resolution per box checked in Article 8.2.3.

## Slide 26: C401-Articles 9-10
Article 9: Termination or Suspension
  New 9.1.1 contemplates negotiation of a Termination Fee and continued use of Instruments of Service Licensing Fee
Article 10: Miscellaneous Provisions
  10.6.1 and 10.7 – Adds confidential information and “savings” clause

## Slide 27: C401-Articles 11-13
Article 11 – Compensation
  No changes
Article 12 – Special Terms and Conditions
  Make sure to include if applicable, delete if not.
Article 13 – Scope of Agreement
  Again, indicates the E203 (BIM and Digital Data Exhibit) is part of the Contract.

## Slide 28: A201-Article 1-General Provisions
1.2.1.1 – “Savings” Clause
1.6 – All notices must be in writing but the provision now recognizes that all required notices, other than Notice of Claims required under Article 15.1.3, can be provided by electronic means (email) if allowed per a provision in the A101 (the Agreement).
1.7/1.8 – BIM and Digital Data transmission similar to B101 requirements.

## Slide 29: A201-Article 2-Owner
2.2 – Article has been significantly changed. The Contractor can now demand confirmation of Owner’s financial viability after commencement of the work if Owner fails to make payments as required, the Contractor identifies in writing a reasonable concern with Owner’s ability to pay, or if a change in work materially changes the Contract Sum.
  Contractor can stop performing all or some of the work until reasonable evidence is provided.
2.2.4 – New provision for situations involving receipt of and disclosure of confidential information.

## Slide 30: A201-Article 3-Contractor
3.3.1 – Attempts to clarify roles of Architect and Contractor regarding means and methods, and safety.
  Contractor is responsible for means and methods unless means and methods are specific instructions provided in the Contract Documents.
  If means and methods are prescribed, the Contractor must evaluate for safety.
  If Contractor provides notice that prescribed means are not safe, Contractor must propose alternative.

## Slide 31
  If Contractor proposes alternative, Architect only evaluates for conformance with the design intent of completed construction.
    Unless Architect objects to Contractor’s alternative, Contractor must perform per its proposed alternative.
      NOTE: Unclear whether Contractor can claim as additional work.

## Slide 32
3.5.2 – Clarifies that all warranties are to be issued in Owner’s name.
3.7.4 – Notice for Differing Site Conditions must now be provided in 14 (versus 21) days.
3.10.1 – Provides for more detail in Contractor’s schedule including interim milestones, apportionment of work by construction activity, time required for completion of each portion of work.
  NOTE: Likely causes additional analysis by Architect as Architect “must review and approve, or take other appropriate action upon Contractor’s submittals …” (See, B101, Article 3.6.4.2) and must promptly report to Owner known deviations from most recent Contractor submittal schedule (See, B101, Article 3.6.2.1).

## Slide 33
3.12.10 – The provision that “the Contractor shall not be responsible for the adequacy of the performance and design criteria specified in the Contract Documents” has been stricken. However, a provision has been added that “the Contractor shall be entitled to rely upon the adequacy and accuracy of the performance and design criteria provided in the Contract Documents.”
  Possibly add provision indicating Contractor’s design professional is responsible for complete review and analysis of performance and design criteria and must provide notice to Architect of any issues that reasonably should have been discovered.

## Slide 34
3.17 – Contractor must now have actual knowledge of a patent infringement to be liable.
3.18 – Indemnification clause needs to be revised to comport with Michigan law for private projects.

## Slide 35: A201-Article 4-Architect
4.2.4 – Most notable change is that Owner/Contractor communications involving Architect’s services or professional responsibilities must include Architect and the substance of all direct communication between Owner and Contractor must be promptly reported to the Architect.

## Slide 36: A201-Article 5-Subcontractors
5.3 – Clarifies subcontract agreements must be in writing.

## Slide 37: A201-Article 6-Construction by Owner or Separate Contractor
6.2.2 – Clarifies that Contractor is not responsible for defective work by others unless the defect is “apparent” to the Contractor.

## Slide 38: A201-Article 7-Changes in the Work
7.3.5 – Clarifies that disputes over adjustments in Contract Time are subject to Article 15 claims procedures.
7.4 – The Contractor can now challenge the Architect’s order that a change is a “minor change in the work.” However, if there is no challenge by the Contractor before the Contractor implements the work, there can be no challenge.

## Slide 39: A201-Article 8-Time
There are no critical changes.

## Slide 40: A201-Article 9-Payments and Completion
9.1.2 – New article provides that in unit price contracts, a material change in quantities that causes substantial inequity in unit prices to either the Owner or Contractor requires a unit price adjustment.
9.2 – Contractor request for changes to the Schedule of Values must be submitted to Architect with written support sufficient for Architect to substantiate the requested revision. Architect must object or else the adjusted Schedule of Values will be utilized for future pay applications.

## Slide 41
9.5.2 – Any party objecting to the Architect’s decision regarding a Pay Application must submit a claim.
9.6.8 – A new provision indicates that as long as Owner has paid Contractor properly, the Contractor is responsible to defend and indemnify Owner from lien claims or other subcontractor demands for payment.

## Slide 42: A201-Article 10-Protection of Persons and Property
There are no significant changes.

## Slide 43: A201-Article 11-Insurance and Bonds
This provision has been significantly altered. A new Exhibit A to the A101 (Contractor-Owner Agreement) now sets forth the Contractor’s and Owner’s insurance requirements.
  Also, 11.2.2 now allows the Contractor to delay commencement of the work in order to allow time to obtain insurance the Owner was supposed to procure and per 11.2.3 can suspend work if the Owner’s insurance is cancelled.

## Slide 44: A201-Articled 12-13
Article 12: Uncovering and Correction of Work
  There are no significant changes
Article 13: Miscellaneous Provisions
  There are no significant changes

## Slide 45: A201-Article 14-Termination or Suspension of the Contract
14.4.2 – Like the B101, the document now references the possibility of including a “Termination Fee” in the A101 in situations involving termination for convenience.

## Slide 46: A201-Article 15-Claims and Disputes
15.1.1 – Clarifies that the Owner’s imposition of liquidated damages is not a claim.
15.1.4.2 – The IDM’s decision on a claim is the basis for Contract Sum and Contract Time adjustments subsequent to the decision (but subject to dispute resolution process).
  There will be push back from Contractors because work cannot be suspended during the dispute resolution process (15.1.4)

## Slide 47
15.3.3 – After a decision by the “Initial Decision Maker”, all claims (other than those which are expressly barred by Contract, which would include claims waived by final payment and claims for consequential damages) must be sent to mediation as was the case under the 2007 document.
  THIS NEW PROVISION THOUGH states that if a party fails to file for binding dispute resolution more than 30 days after mediation has been concluded without resolution or 60 days after mediation has been demanded without resolution, the decision of the IDM is binding.
  While hasty resolution of disputes is a positive, this process is too quick.